# Step-by-step: from here to published

A chronological runbook. Every step says who does it, what to do, how long it takes, and what to expect next. paper/submission-packet.md is the companion document — it maps files to upload slots. This one is the order of operations.

Nothing below is urgent. The preprint step protects you regardless of how long the rest takes.

## Stage 0 — Pre-flight (15 minutes, either author)

Confirm the deliverable still builds and passes its own checks.

cd /Users/e/grammar-of-immunity
python3 paper/build.py                     # rebuilds DOCX + HTML from the markdown
python3 paper/check_highlights.py          # expect PASS
.venv/bin/codespell paper/*.md README.md   # expect no output
cp paper/build/manuscript.docx paper/TCR_Manuscript_V3.docx

Then open paper/TCR_Manuscript_V3.docx and read it once end to end. Not to check the numbers — those are verified — but to hear the sentences. This is the last point where changing your mind is free.

Done when: the DOCX opens, figures appear, and you have both read it.

## Stage 1 — Post the preprint (20 minutes, Erick)

Go to https://www.biorxiv.org/submit-a-manuscript and create an account with erick.tejkowski@gmail.com.

Work through the form using the table in paper/submission-packet.md. The answers that people get wrong:

- Category: Bioinformatics. Not Immunology. The paper’s audience is methods-minded readers.

- License: CC-BY 4.0. It does not affect journal submission afterward.

- Submitted to a journal? No. That is true today and stays true until Stage 5.

- Authors in order: Erick, then Maria. bioRxiv freezes this into the citation.

Upload paper/TCR_Manuscript_V3.docx. If it asks for figures separately, use paper/figures/*.png.

Immediately after submitting, tell Maria to watch for an email from bioRxiv asking her to confirm authorship. The posting does not proceed until she clicks it. This is the single most common cause of a stalled preprint.

Done when: you see “submitted” status and Maria has clicked her link.

## Stage 2 — Screening (1–2 days, no action)

A bioRxiv staff member checks that this is life-science research, is not plagiarized, contains no patient-identifying data, and makes no dangerous claims. It is not peer review. Rejection here is rare and is usually about category or file format.

What arrives: an email with your DOI, formatted like 10.1101/2026.08.03.xxxxxx.

## Stage 3 — Record the DOI (5 minutes)

Two files need it:

- paper/cover-letter.md — replace DOI: XXXX

- README.md — add it near the top

Then python3 paper/build.py and re-copy the DOCX, so the manuscript and the letter agree. The assistant can do this in one pass if you paste the DOI.

Why it matters: from this moment you have a timestamped, citable record with both your names on it, independent of any journal’s decision. Whatever happens next, the work is yours and it is public.

## Stage 4 — Journal preparation (1 hour, Erick)

Open ImmunoInformatics’ guide for authors in a browser: https://www.elsevier.com/journals/immunoinformatics/2667-1190/guide-for-authors

That page blocks automated access, so four things are unresolved. Find and copy these sections:

- Abstract word limit — ours is 264. If the cap is 250, cut the TCRdist parenthetical.

- Whether structured-abstract headings are fixed. Ours end with “Validation”, which is non-standard.

- Whether Highlights are required, and their character limit. Five are ready.

- Reference style, and whether figure captions belong in the manuscript or a separate file.

Also read their generative-AI policy. Your declaration is already in the manuscript before the references. Read how they frame it so you are not surprised later.

Paste those sections to the assistant; the files get conformed in one pass.

Done when: the abstract is within their limit, headings match their format, and the highlights file is saved as .docx.

## Stage 5 — Submit to the journal (45 minutes, Erick)

Create an Editorial Manager account for ImmunoInformatics. Upload, in this order:

| Item | File |
| --- | --- |
| Manuscript | paper/TCR_Manuscript_V3.docx |
| Highlights | paper/highlights.md saved as .docx |
| Figures | paper/figures/vector/*.pdf |
| Cover letter | paper/cover-letter.md, adapted using the ImmunoInformatics note in that file |

In the cover letter, state the preprint DOI. Declare no competing interests and no funding. If it asks for suggested reviewers, use the guidance at the bottom of the cover letter, and do not name anyone either of you has corresponded with.

The system will generate a PDF proof of your submission. Read it before approving — Editorial Manager mangles tables and special characters more often than you would expect, and β and en-dashes are the usual casualties.

Done when: status reads “submitted to journal” or “with editor”.

## Stage 6 — Waiting (2 weeks to 6 months)

Editorial Manager statuses, in the order you will probably see them:

| Status | Meaning |
| --- | --- |
| With Editor | An editor is deciding whether to send it out |
| Under Review | Reviewers have accepted the invitation |
| Required Reviews Complete | Reports are in; the editor is deciding |
| Decision in Process | A letter is coming |

DOAJ lists this journal’s median submission-to-publication time at 23 weeks. A desk rejection, if it happens, usually arrives within two weeks and means the editor judged it out of scope rather than unsound.

Do not email to ask about progress before eight weeks. After twelve, a short polite query is normal.

## Stage 7 — The decision

Four possible outcomes.

Major revision. The most likely, and it is a good outcome — it means they engaged. Expect requests for one or more of: a comparison against TULIP or TCRen, a VDJdb confidence-score replication, more detail on negative-example construction, or a defense of the linear model class. All four are already disclosed in Limitations, so none is a surprise. Go to Stage 8.

Minor revision. Clarifications and wording. Usually a week of work.

Reject and resubmit. Not the same as rejection. They want substantial new work but would look again. Treat it as Stage 8 with a longer timeline.

Rejection. Go to Stage 9.

## Stage 8 — Revision (1–6 weeks depending on what they ask)

The mechanics that matter:

- Write a point-by-point response letter. Quote each reviewer comment, then answer directly beneath it. Say exactly what changed and give the section and line. Reviewers look for whether you took them seriously.

- Where you disagree, say so with evidence, politely. “We respectfully disagree, for the following reason” is normal and expected. Capitulating to a comment you believe is wrong makes the paper worse.

- Supply a tracked-changes version as well as a clean one, if they ask.

- Run any new analysis in the repository, not by hand, so the number in the response letter and the number in the code are the same thing.

The likely requests and their real cost, for planning:

| Request | Cost | Notes |
| --- | --- | --- |
| VDJdb confidence-score replication | 1–2 days | needs the official release file, not the chunk records; will shift Table 1 slightly |
| Comparison against TULIP | 2–4 weeks | unsupervised, needs its own harness; no negative examples |
| Comparison against TCRen | 3+ weeks | needs structural models per pair |
| Clarify negatives / model class | 1 day | text only; the controls already exist |

## Stage 9 — If rejected

Nothing about a rejection invalidates the work, and your preprint stays up.

Next venue, in my order of preference:

- Frontiers in Immunology, Systems Immunology or Methods section. Reaches many more readers and is PubMed-indexed, but the APC is CHF 3,150 — roughly twice ImmunoInformatics — and their fee-support program does not cover US authors. Reframe the cover letter to lead with the immunology: the batch-effect finding and the germline-versus-junctional decomposition.

- A zero-cost hybrid such as Briefings in Bioinformatics or Bioinformatics, declining the open-access option so there is no charge. Both are PubMed-indexed. The accepted version sits behind a paywall while your preprint stays free. Confirm current pricing before relying on this.

- PeerJ or BMC Bioinformatics. These judge soundness rather than novelty, which suits this paper. Emphasize the control architecture.

Whichever you choose, incorporate anything useful the first set of reviewers said, even if they rejected it. Free peer review is still peer review.

## Stage 10 — Acceptance

- Pay the APC. ImmunoInformatics is USD 1,900. DOAJ lists a waiver policy; as unaffiliated authors with no funding, ask about it explicitly before paying.

- Proofs arrive within about two weeks. Check the tables character by character — typesetters re-key numbers, and this paper is mostly numbers. Confirm β renders, the en-dashes in ranges survive, and every CI bracket is intact.

- Update the preprint. Post the accepted version to bioRxiv as v2; the original stays visible and the DOI still resolves.

- Add the published DOI to the README and the repository description.

## Timeline, realistically

| Stage | Elapsed |
| --- | --- |
| Preprint live with a DOI | 1–3 days |
| Journal submission complete | within a week |
| First decision | 6 weeks to 6 months |
| Revision and resubmission | plus 2–8 weeks |
| Acceptance to publication | plus 4–8 weeks |

Roughly six to twelve months to a published paper, and about three days to a citable one. That gap is the reason to do Stage 1 tonight and Stage 5 whenever you are ready.